## WBS
Work Breakdown Structure (WBS) for AWS Deployment and Automation
Project Duration: 3-4 months |  |  |  | Man days
# | Epic/Task | Tentatives | Details | Effort (mds) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1 | Proof of Concept (POC) with AWS Cloud |  |  | 20 | bar: W1 to W4
| Project Kick-off and Planning |  |  | 10 | bar: W1 to W2
Define project scope, objectives, and success criteria | bar: W1
Define migrate strategy (rehost, replatform,...) | bar: W1
Define project standards (coding, infrastructure,...) | bar: W2
| Incremental Development and Validation |  |  | 10 | bar: W3 to W4
Build infrastructure templates | bar: W3
Build CI/CD flow templates | bar: W4
2 | Infrastructure |  |  | 20 | bar: W5 to W8
| Essential module |  |  | 10 | bar: W5 to W6
Develop Terraform essential module: Network, K8s cluster | bar: W5
Develop Terraform load balancer module | bar: W6
Develop Terraform storage module | bar: W6
| Component module |  |  | 10 | bar: W7 to W8
Develop Terraform security module: Firewall, Certificate | bar: W7
Develop Terraform IAM module: User, Group, Policy, Role,... | bar: W8
3 | Refinement |  |  | 20 | bar: W9 to W12
| Microservices Deployment |  |  | 15 | bar: W9 to W11
Containerize for microservices | bar: W9
HelmChart deployment | bar: W10
Test container deployment and scaling | bar: W11
| Domain |  |  | 5 | bar: W12
Set up global custom domain routing | bar: W12
Configure location-based routing | bar: W12
Test global routing | bar: W12
4 | Monitoring/Logging & Handover |  |  | 20 | bar: W13 to W16
| Microservices |  |  | 15 | bar: W13 to W15
|  | Microservices monitoring deployment |  | 10 | bar: W13 to W14
|  | Agent | Requirement: Docker, docker-compose,... | bar: W15
Uptime, Node metrics: Blackbox, NodeExporter | bar: W15
|  | Centralize | Requirement: Docker, docker-compose,... | bar: W15
Monitoring: Prometheu | bar: W15
Dashboard: Grafana | bar: W15
Alert: Alert Manager | bar: W15
|  | Microservices logging deployment |  | 5 | bar: W16
AWS | bar: W16
AWS monitoring deployment | bar: W16
AWS logging deployment | bar: W16
80